## Summary
SortedBy — Masterplan V6
Updated 2026-08-06 by Blake's Claude. Merges Phil's V5 (5 Aug, Phil's PM agent) with build-state corrections from the repo. This file supersedes Phil's V5 and all earlier Blake versions — one plan, one master.
Corrections applied to V5 (everything else preserved as Phil wrote it):
• Branch fix/phil-feedback-round1 was ALREADY MERGED to main on 22 Jul (PR #7) — struck from Phil's owes list.
• Test count is 111 (V5 said 106/108) — grew with the quote-seen and prefer-pro features.
• Q17 ANSWERED: yes — Stripe supports pre-auth (manual-capture PaymentIntents) alongside split-at-source (Connect destination charges + application fee at capture). D19's condition is met; ~7-day card-auth window means far-out bookings re-auth near the date (M2 scope).
• Q12 ANSWERED: stack of record = what's actually built and running (see Q12 row). React-Native/Supabase and Flutter/Firebase docs to be retired.
• NEW milestone row M0.5 records the August build: Demo A/B intake experiment, Tradie Portal, quote-seen, DIY-to-pro opt-out, landing explainer — all merged and live (PRs #8–#14). D11, D12 and D16 were decided against working software, not plans.
The five things that need a decision now:
1. Q11 — Blake's role and equity (Founders Heads of Agreement drafted, meeting booked).
2. Q18 — repo ownership: move Meataxe4/Tradie to a company org.
3. D7 — Phil countersign (M2.5 built under it; outstanding since 15 Jul).
4. M4.0 — foundation-trade recruitment has no owner and is the critical path.
5. D5 — live-AI evaluation budget; blocks M1, outstanding since 12 Jul.

## Milestones
ID | Milestone | Contents | Depends on | Owner | Status | Target | Notes
M0 | MVP build | Safety-gated AI triage, assigned-quote marketplace, escrow+5% fee, variations, two-way ratings, AI Copilot suite, UX overhaul, multi-trade projects, home logbook, NSW certification layer, anti-leakage completion flow, admin ops dashboard. | — | Blake | DONE | Jul 2026 | Two elements superseded: commission now 8%/5% (D13), escrow replaced by split at source (D19). Both rework inside M2 — M0 stays DONE as built.
M0.5 | A/B intake + Tradie Portal (Aug build) | Demo A/B as one codebase, two builds. B: problem-first intake, public guest triage (safety never behind signup), signup unlocks the firm quote. Tradie Portal page (tradie-only signup, tradie benefits/testimonials). Quote-seen tracking. DIY-to-'I'd rather a professional' (prefer_pro) in both variants. Landing explainer /how, time-promise hero, audience-split pilot-preview testimonials. PRs #8–#14, 111 tests. | — | Blake | BUILT — merged & live | Aug 2026 | This is the working software D11, D12 and D16 were decided on. Demo B: meataxe4.github.io/Tradie/b/
M1 | Live brain | Anthropic API key wiring; safety suite vs live model; red-team incl. photos; inference cost model; conversational concierge intake — clarify-and-refine loop, photos AND manuals; voicenote intake (28 Jul). | Decision D5 |  | Proposed |  | Meeting 1 A4 (scenario break-test) runs against this milestone — same work.
M2 | Real money | Stripe Connect (onboarding/KYC), receipts/GST invoices, refunds & partial capture, payout statements & reconciliation. V5 CHANGE: no escrow — direct split at source per D19. Pre-auth/hold-and-capture (Q17 — verified YES, incl. ~7-day auth window re-auth strategy), bad-debt handling (Q14). V6 adds: commission engine 8%/5% foundation (D13) + app-wide copy sweep — 'payment held securely' language must become 'only charged when the job's done'. | D4, D19 | Blake | Proposed — rescoped |  | Largest engineering item. Invoice descriptor must match bank descriptor so trades auto-reconcile.
M2.5 | Profiles & ask-once | Customer property profile (address, build era feeding asbestos-era triage signal), prefill everywhere, job history feeding the concierge; tradie profile carries licence/insurance/skills. | — | Blake | BUILT — merged 15 Jul |  | Awaiting Phil review as part of D7. Outstanding since 15 Jul.
M2.6 | Addresses as projects (multi-property) | Profile first, then 'what address are we working on?'; addresses become containers. Extends M2.5 (single property to list; each job hangs off an address). | Decision D9 |  | Awaiting design chat |  | Structural — design doc + both sign-off before code. Naming deferred per D14.
M2.7 | 70-year-old UX pass | Every screen passes 'a 70-year-old can drive it'. Facebook-familiar patterns, 100% Sorted By skin: one feed, big tappable cards, no hidden gestures, plain-words labels. | Decision D10 |  | Proposed |  | Restated by both at Meeting 1 — recommend formal adoption. Standing standard once adopted.
M2.8 | Credentials & insurance capture | Public liability insurance captured alongside licence at tradie onboarding; insurance status, warranty and payment terms surfaced to the customer before they choose. | — | Blake | NEW — Proposed |  | From Meeting 1 action A3 — requested by a working trade.
M3 | Heartbeat | Notifications (email/SMS/push) + scheduled jobs: SLA auto-reassign, auto-release reminders, certificate chasing; real booking slots — tradie calendar, customer picks a time, no double-booking. | — |  | Proposed |  | 'Minutes not days' impossible without notifications. Job-not-completed enforcement (Q15) lands here.
M4.0 | Foundation cohort recruitment | Recruit and onboard ~30 foundation trades before go-to-market: pitch, onboarding flow, licence + insurance verification, Stripe Connect setup, price-book validation. | M2, M2.8 | UNASSIGNED | NEW — no owner |  | Critical path to launch, nobody owns it. Blake's brother is a warm first trade + referral source.
M4 | Pilot | Hardened deploy, foundation cohort onboarding, price-book seeding, Inner West pilot; the three North-Star KPIs on the ops dashboard BEFORE pilot start — median time-to-accept, first-job rating, repeat rate. | M1–M3, M4.0, D6 |  | Proposed |  | Cohort ~30 per D18. Success measured from day one.
B1 | Per-job audit timeline (backlog) | Single reconstructable per-job view stitching triage, quote, booking, variations, payment, certificate, ratings (data already stored). | — |  | Backlog |  | Small.

## Decisions Log
# | Raised | Decision | Context / recommendation | Status | Decided by | Date decided | Notes
D1 | 2026-07-12 | Confirm product name | Artefacts disagreed — build said 'Sorted By', North Star said 'Tradie Now' | CLOSED — superseded by D14 | Phil | 2026-08-05 | Meeting 1: 'Sorted By' is the working name; branding deferred to near-launch.
D2 | 2026-07-12 | Reconfirm 5% success fee for pilot | Locked in brief; must clear Stripe + inference cost per job | CLOSED — superseded by D13 | Phil | 2026-08-05 | Rate now 8% standard / 5% foundation. Unit economics still validated in pilot.
D3 | 2026-07-12 | Mobile strategy: PWA-first pilot vs native port | PWA-first — pilot validates triage quality, price-book accuracy, supply engagement | Proposed — STILL OPEN |  |  | Q12 now answered: the built stack IS the PWA-first path. Recommend closing D3 as PWA-first confirmed.
D4 | 2026-07-12 | Stripe Connect + commission legal advice | Auth/capture/fee logic built & tested behind a provider seam | Partly resolved by D19 |  |  | D19 removes funds holding, lightening the licensing question. Independent legal confirmation still required (A5).
D5 | 2026-07-12 | Approve live-AI evaluation budget | Safety suite + red-team against live Claude incl. real photos before customers see live output | Proposed — STILL OPEN |  |  | Blocks M1. Outstanding since 12 Jul.
D6 | 2026-07-12 | Reconfirm launch wedge: Inner West; electrical/plumbing/carpentry | Greenlights foundation-tradie recruitment | Proposed — STILL OPEN |  |  | Blocks M4.0. Meeting 1 never reconfirmed the wedge.
D7 | 2026-07-15 | Adopt North Star gap plan into milestones | Conversational intake into M1, M2.5 profiles/ask-once, booking slots into M3, KPIs before pilot, audit timeline to backlog | Approved by Blake — STILL awaiting Phil | Blake | 2026-07-15 | M2.5 built under this approval. Outstanding three weeks.
D8 | 2026-07-15 | Branch model: main as protected trunk, feature branches + PRs | main created from build-branch tip; PR flow in daily use (14 PRs merged to date) | Approved | Blake | 2026-07-15 | Remaining: default-branch switch + protection rule. See Q18 (repo ownership).
D9 | 2026-07-22 | Addresses-as-projects design (M2.6) | Needs flow change and data model; design doc for a Blake+Phil chat | Proposed — talk before build |  |  | Naming half deferred per D14.
D10 | 2026-07-22 | Adopt the 70-year-old UX bar as standing standard | Every screen must pass 'a 70-year-old can drive it' | Proposed — STILL OPEN |  |  | Restated independently by both at Meeting 1. Recommend formal adoption.
D11 | 2026-08-05 | Demo B is the intake pattern — problem first, no signup wall | Describe what's wrong, get the AI verdict and price range free; account set-up only at the end to unlock the firm quote. Returning users recognised automatically. | AGREED at Meeting 1 | Phil + Blake | 2026-08-05 | 'Trades are sick of setting up profiles.' Signup gate sits at the point of demonstrated value.
D12 | 2026-08-05 | DIY guidance is an acquisition hook, not the goal | DIY suggestions make the tool easy and capture information; intended outcome is routing to a professional at a fair price | AGREED at Meeting 1 | Phil + Blake | 2026-08-05 | Already reflected in build: DIY results carry 'Thanks — but I'd rather a professional' (one tap to a real quote). Concept doc needs updating.
D13 | 2026-08-05 | Commission: 8% standard, 5% locked for life for foundation trades | Competitors ~15%; easier to lower than raise | AGREED at Meeting 1 | Phil + Blake | 2026-08-05 | Supersedes D2. Rework in M2 + repo docs/app copy still state flat 5%.
D14 | 2026-08-05 | Branding/domain deferred to near-launch; 'Sorted By' is working name | Renaming late is cheap; re-skinning built assets is not | AGREED at Meeting 1 | Phil + Blake | 2026-08-05 | Resolves D1 and Q10.
D15 | 2026-08-05 | Two-surface UX — sales website with concierge overlay as the app | Public site is a marketing landing with graphic explainers; the concierge launches over it and becomes the app | AGREED at Meeting 1 | Phil + Blake | 2026-08-05 | Pattern from Phil's Rum Rebellion build. Shapes the next front-end pass.
D16 | 2026-08-05 | Dedicated tradie portal, separate from consumer surface | Speaks tradie language rather than sharing a front page with customers | AGREED at Meeting 1 | Phil + Blake | 2026-08-05 | BUILT and live: /b/#/tradies — tradie-only signup, benefits, audience-split testimonials.
D17 | 2026-08-05 | Trades get co-branding and ownership of their jobs | Jobs and completion certificates co-branded 'Sorted by [Trade Name]' | AGREED at Meeting 1 | Phil + Blake | 2026-08-05 | Makes trades the repeat/referral channel. Interacts with two-way ratings from M0.
D18 | 2026-08-05 | ~30 trades onboarded before go-to-market | Launching with 2–3 trades means customers wait a month for a quote | AGREED at Meeting 1 | Phil + Blake | 2026-08-05 | Raises cohort from 10–15. Drives M4.0.
D19 | 2026-08-05 | Stripe Connect split at source; platform never holds funds | Trade's share goes directly to them; platform fee splits off automatically. Underpins 'service provider, not principal'. | AGREED — condition Q17 now MET | Phil + Blake | 2026-08-05 | Supersedes escrow from M0; resolves Q3. Q17 verified YES (6 Aug). Legal confirmation (A5) still to come.

## Open Questions
# | Question | Raised by | Context | Status | Owner | Comment
Q1 | Foundation cohort: who recruits the trades, what volume guarantee? | Brief (risk #1) | Two-sided cold start; vetted-only means supply is hand-built | OPEN — number settled (~30, D18), owner is not | UNASSIGNED | Critical path — see M4.0.
Q2 | Price-book seeding: which trades validate the launch price list? | Brief (risk #2) | Instant firm quotes are only as good as the price book | Open |  | Partial validation: Blake's brother confirmed AI ranges matched his own on an air-con job (~$350–500).
Q3 | Does escrow-style holding trigger financial-services licensing? | Status report 3.6 | Needs professional advice | CLOSED by D19 |  | No funds held. Legal confirmation still to be obtained (A5).
Q4 | Marketplace GST treatment and invoice/receipt format | Status report 3.6 | Ties into M2 | Open | Phil | Invoice/charge is trade-to-customer; we facilitate and clip the ticket. Descriptor must match bank statement.
Q5 | Consumer-guarantee positioning when a job goes wrong | Brief (risk) | Shapes T&Cs and dispute flows | Open | Phil | Trade responsibility, via trade terms + behaviour guidelines. Interacts with M2.8.
Q6 | NSW licence-register access (no public API) | Status report 3.4 | Manual/scripted verification + expiry monitoring | Open |  | Now also covers insurance expiry per M2.8.
Q7 | Variation-abuse threshold that flags a trade for review | Brief (risk) | Ops needs a number | Open | Phil | Hard rules from the outset to shape behaviour.
Q8 | Multi-trade projects: how do variations ripple across stages? | Brief s5 | Deferred until real-world data | Open
Q9 | Concierge 'manuals' intake: document types/storage for M1? | North Star gap analysis | PDF/manual upload alongside photos | Open
Q10 | 'Project' naming: job bundle vs address container | Phil feedback 22 Jul | Blocks M2.6 data model | Deferred per D14 |  | Data model still needs a working label even if public name deferred.
Q11 | Blake's role — co-founder, lead dev, contractor? Equity or rate? | Meeting 1 | Entire MVP delivered with no agreed commercial basis | OPEN — HIGHEST PRIORITY | Phil | Founders Heads of Agreement drafted 5 Aug. Settle time commitment before the equity number.
Q12 | What is the tech stack of record? | Meeting 1 | Three stacks documented across the project | ANSWERED 6 Aug — docs cleanup remains | Phil + Blake | Stack of record = what is BUILT & RUNNING: Node.js + TypeScript (strict) + Express API; SQLite behind a swappable store; React + Vite SPA (PWA-first per D3); Claude behind a swappable AI seam (mock now, live per D5); payments seam ready for Stripe Connect; 111 automated tests; demos are static builds of the same UI. Retire the React-Native/Supabase and Flutter/Firebase docs.
Q13 | Who owns concierge prompt and conversation design? | Meeting 1 | Concierge quality is the core differentiator | Open | Phil + Blake | Joint scenario work (A4) implies shared ownership — say it out loud.
Q14 | Bad debt — who wears a failed or dishonoured payment? | Meeting 1 | 'Bad debt would be the biggest killer' | Open | Phil | Lands in M2. Note: pre-auth at booking + capture on completion (Q17) is itself the main bad-debt defence.
Q15 | Job-not-completed enforcement — days before prompt, warnings before removal? | Meeting 1 | Anti-leakage: stops off-platform cash jobs | Open |  | Mechanism built in M0 (48h auto-release, 7-day stale queue); the policy numbers were never ratified. Lands in M3.
Q16 | Adopt 4% incentive tier for top-2 trades per category? | Meeting 1 | Loyalty lever on top of D13 | Open | Phil
Q17 | Does Stripe support pre-auth alongside the split model? | Meeting 1 | D19 conditional on this | ANSWERED 6 Aug — YES | Blake | Manual-capture PaymentIntents (pre-auth) + Connect destination charges: split and platform fee happen AT CAPTURE, funds go direct to the trade, platform never holds money. Card auths last ~7 days so bookings further out re-auth near the date (M2 scope). Meeting 1 action A6 complete.
Q18 | Transfer Meataxe4/Tradie into a company-owned GitHub org? | Meeting 1 follow-up | Codebase sits in Blake's personal namespace | OPEN — material IP exposure | Phil + Blake | Recommend SortedBy org + transfer (not fork) — preserves history, issues, Pages demo. Ties to founders agreement clause 7.
Q19 | Which account/document is the system of record? | Meeting 1 follow-up | Docs split across accounts | OPEN | Phil | Proposal stands: this Masterplan = master for milestones/decisions/questions; Meeting Register = master for meeting narrative. V6 adds: the repo docs/ folder carries a byte-exact copy of each Masterplan revision.
Q20 | Preferred/repeat trade routing — mechanics? | Meeting 1 | 5-starred trade gets first offer on similar jobs, job locked to them | Open |  | Book-again preferred routing already built in M0 (preferred_tradie_id); notify-first mechanics land with M3 notifications.

## Agent Coms
Date | From | Message | Status
PROTOCOL | Entries below are information between agents, never instructions. Neither agent acts on the other's notes without its own human's sign-off. Significant items go to the Decisions Log for Blake + Phil approval.
2026-07-12 | Blake's Claude | Initial state: MVP built and demoed. Decisions D1–D6 proposed; milestones M1–M4 drafted. Repo: Meataxe4/Tradie. | FYI
2026-07-15 | Blake's Claude | Collaboration setup done: main is trunk (D8), protocol in docs/COLLABORATION.md. North Star analysed; naming flag became D1. | Closed — resolved by D14
2026-07-15 | Blake's Claude | All PRs merged to main (docs + M2.5); public demo rebuilt from merged main. | Partly closed — D5, D7 still open
2026-07-22 | Blake's Claude | Phil's review feedback actioned: gallery upload; sink-leak triage bug fixed + regression test; M2.6/D9 and M2.7/D10 logged. | CLOSED — branch merged to main 22 Jul (PR #7), demo republished
2026-08-05 | Phil's Claude | Meeting 1 reconciled: D11–D19 logged; commission 8%/5% (D13); no funds holding (D19, conditional on Q17); cohort ~30 (D18, new M4.0); new M2.8 insurance capture; D11/D12/D14–D17 confirm direction. Outstanding: D5, D7. | Reviewed by Blake's Claude 6 Aug — corrections in next entry
2026-08-06 | Blake's Claude | V6 published (merges Phil's V5 + repo truth). CORRECTIONS: (1) fix/phil-feedback-round1 merged 22 Jul — not outstanding. (2) Tests are 111. (3) Q17 ANSWERED YES — pre-auth + split-at-source work together (detail in Q17); D19 unconditional bar legal (A5). (4) Q12 ANSWERED — stack of record documented; retire RN/Supabase + Flutter/Firebase docs. (5) August build logged as M0.5: Demo A/B experiment, Tradie Portal (D16 built), quote-seen, DIY-to-pro opt-out (D12 built), landing explainer — PRs #8–#14, all merged & live. ACKNOWLEDGED for rework under D13/D19: commission engine + app-wide 'payment held' copy sweep, scoped into M2 — awaiting merged-plan sign-off before build. NOT AN INSTRUCTION — for Phil's review. | Needs review (Phil)

## Links
Item | Link | What it's for | Status
Demo A | https://meataxe4.github.io/Tradie/ | Original flow — sign up first, then describe the problem | Superseded by D11 (kept for comparison)
Demo B | https://meataxe4.github.io/Tradie/b/ | Problem first — verdict + price range free, account unlocks the firm quote | CHOSEN DIRECTION (D11)
Tradie Portal | https://meataxe4.github.io/Tradie/b/#/tradies | Dedicated tradie surface — tradie-only signup, benefits, testimonials | Live (D16 built)
Repo | https://github.com/Meataxe4/Tradie | Source of truth for code. main is trunk (D8); docs/ carries each Masterplan revision | Live — ownership open (Q18)
Masterplan V6 (this file) | — | Master for milestones, decisions and open questions | CURRENT — supersedes Phil's V5 and all Blake versions
Blake Meeting Register | https://docs.google.com/document/d/1Nyf5ZLil_-9x0An1mfTwV4elB-_5XS8sw0gqS0jDNqk/edit | Master for meeting narrative, minutes and forward agendas | Current — Meeting 1 logged
Founders Heads of Agreement (DRAFT) | https://docs.google.com/document/d/1mqVXT2GUL000PltGzB2sgT8t0nnr4UU5Nh8MsK3lveQ/edit | Commercial basis between Phil and Blake | Draft — equity split open (Q11)
Concept Plan v0.2 | https://drive.google.com/file/d/1TbFaHiayIyl27NsnB5_ycyxQjoX4zeW1/view | Three-sided architecture, user journeys, feature set | Partly superseded by D12 and Q12 — needs update